## Sheet1
we will use the same case of app for resturants we will assume that we are in the seventh iteration
30 hr per iteration(two weeks) 9 iterations
to do | in progress | done
add any recommended features | deliver first proto type | sign in/up page for customer
test app |  | sign in/up page for resturants
launch |  | Gui for the app
updload available data for resturant
iterations | ideal | practical
1 | 80 | 85
2 | 70 | 70
3 | 60 | 55
4 | 50 | 50
5 | 40 | 40
6 | 30 | 35
7 | 20 | 15
8 | 10 | 7
9 | 0 | 0